## Slide 1
GMP Pacific Midterm Workshop
The Institute of Applied Sciences
17-18 September 2018
Brisbane

## Slide 2: The Institute of Applied Sciences
Analytical laboratory Services is one of the 6 Units
ISO17025 and IANZ accredited laboratory
Developed as one of the 6 regional reference laboratories for GMP POPs and the only one in the PIR
Service to local, regional and international clients/partners
Analyses related to environment, trade and health

## Slide 4: Overview of activities (GMP 2)
Air sampling (PUFs)
Surface water sampling
Human milk
National samples
Administration and logistical support

## Slide 5: Facilities at IAS-USP
Dedicated technicians (sampling)
Transportation (4X4 vehicles)
Sampling gear (storage and retrieval)
Human resource (Admin and Scientific)
Equipment (1 X GC-µ ECD and POPs standards)
Regional laboratory for 12 member counties
USP has 14 campuses in the region (logistics)

## Slide 6: Progress to-date
Air sampling (3rd sampling round – To be sent by September 2018)
Surface water sampling (2nd sampling round – To be sent by September 2018)
Human milk (awaiting ethical approval)
National samples (eggs, fish, water, sediment – by October 2018?)
Reporting (financial, workshops, photos)

## Slide 7
Surface water sampling site

## Slide 8
Air sampling site – Nausori met office

## Slide 9: Challenges and solutions
Logistics (access to sites, transportation)
Approval process (ethical clearance)
Dedicated staff (sampling activities)
POPs analysis (training and standards)

## Slide 10: Lessons learnt
GMP 1 vs GMP 2 (regional and individual)
Logistics (sampling, storage, transport)
Regional coordination (point of contact)

## Slide 11: Benefits from GMP
Working towards baseline data
Increased awareness
National Policies
Enhanced Human capacity - Training and capacity building through projects implementation

## Slide 12: Opportunities from GMP
Development of a training programme
Short technical courses for the region
USP – premier tertiary and vocational education provider in the Pacific

## Slide 13: Considerations for sustainability
Training materials could be embedded in USP existing programmes or new programmes
Capacity building (train the trainer)
Support for a regional reference laboratory for testing legacy POPs (i.e. DDT, DDE, etc)

## Slide 14: Vinaka